# Autumn Camping Season | Agency Campaign Brief (v0.9, pending client sign-off)

From: Photon Marketing Agency, PM Yanting Chen | To: MUYE Marketing, Siyu Lin | Length: full version, please summarize

# 1. Goals & KPIs

Window: 2026/9/15-10/15, theme 'Autumn Camping Season', featuring the scented candle series, ambience lamp and bundle.

Revenue goal: NT$4.8M total, new products >= 35%.

Traffic goal: 250K unique site visitors, EDM open rate >= 28%, social engagement >= 6%.

Member goal: +8,000 members, repurchase rate +5 pts.

# 2. Channel Split & Timeline

| Week | Focus | Owner |
| --- | --- | --- |
| W1 (9/15-) | Teaser short video, KOL unboxing, first EDM | Agency + MUYE social |
| W2 | Site hero live, bundle push | MUYE ecom + design |
| W3 | Member-only bonus, pop-up store | MUYE CRM + retail |
| W4 (-10/15) | Final countdown, inventory clearance, wrap-up | All |

# 3. Budget (ex-tax, NT$)

| Item | Amount | Share |
| --- | --- | --- |
| Digital ad spend | 1,200,000 | 48% |
| KOL / short video | 650,000 | 26% |
| Design & assets | 350,000 | 14% |
| Pop-up & gifts | 300,000 | 12% |

# 4. Decisions Needed from Client (MUYE)

Keep bundle at NT$1,880, or add a first-week flash price of NT$1,780? (affects margin and EDM copy)

Member bonus gift, pick one: fragrance travel set OR camping pouch; decide before 9/5 for sourcing.

Pop-up city: Taipei Xinyi vs Taichung Qinmei; pick one (rent and window differ).

Enable Claude/OpenAI-generated social copy drafts for internal review?

# 5. Risks & Contingency

Stock risk: lamp supplier lead time is 3 weeks; if delayed, fall back to candle series as hero.

Rising ad cost: peak-season CPM expected +12%; keep 10% budget flexibility.

Weather risk: prolonged rain weakens camping scenes; prepare 'home camping' alternative assets.

# 6. Measurement & Reporting

Weekly performance report every Wednesday (traffic, conversion, ROAS, inventory).

Full QBR review and next-season recommendation within 5 business days after the season ends.