## Slide 1
Zava Anniversary Sale War Room Deck
Launch 2026/11/06 (Fri) 120 stores nationwide
Regional Operations Ya-Ting Lin, Regional Operations Manager
War Room No. 3 Data as of 2026/10/12

## Slide 2
Agenda
Zava Retail
Zava Anniversary Sale Campaign war room deck Internal use only
2
1
Campaign overview and targets
5 min
2
Store readiness status
15 min
3
Risks and action tracking
15 min
4
Confirm decisions
10 min
5
Next two weeks
5 min

## Slide 3
Campaign overview
Zava Retail
Launch 11/06; forecast campaign revenue NTD 500 million
Zava Anniversary Sale Campaign war room deck Internal use only
3
Forecast campaign revenue
NTD 500M
Three featured bundles
Top-10 stores by revenue
10
45.6% of forecast (NTD 228M)
POS pricing cut-off
11/03 18:00
T-3; later changes miss the weekend batch
• Featured this campaign: Food Storage Set, Storage Basket, Thermos bundles
• Last war room decision: the top-10 stores by revenue must be fully prepared before launch
• Definition: a store is 'Ready' when POS pricing, display, staffing and stock are all complete
• Decision today: confirm whether to launch on the original date and assign owners for not-ready stores

## Slide 4
Store readiness overview
Zava Retail
Data as of 10/12 By store count
Zava Anniversary Sale Campaign war room deck Internal use only
4
Overall readiness
91.7%
Ready 110 / 120 Threshold 90%
Chart: 
| North | Central | South | East
Ready | 38 | 29 | 25 | 18
Not ready | 2 | 1 | 5 | 2
Conclusion: 91.7% by store count;
launch can proceed on the original date.
10 stores not ready, each with an owner and target date.

## Slide 5
Not-ready store details
Zava Retail
10 stores; forecast revenue in NTD million
Zava Anniversary Sale Campaign war room deck Internal use only
5
Store | Region | Forecast revenue | Open item | Owner | Target date
S014 Taipei Beitou | North | 22.0 | POS pricing | Chih-Ming Wang | 10/30
S008 Zhonghe Jingan | North | 20.0 | POS pricing | Chia-Jung Li | 10/30
S056 Taichung Fengyuan | Central | 18.0 | POS pricing | Chien-Hung Chou | 11/02
S071 Tainan Jiali | South | 1.5 | Display delivery | Yi-Ting Kuo | 11/03
S078 Kaohsiung Zuoying | South | 1.5 | Staff roster | Wen-Chieh Hsu | 11/03
S083 Chiayi City | South | 1.5 | Display delivery | Ya-Wen Cheng | 11/04
S090 Kaohsiung Daliao | South | 1.5 | POS pricing | Ming-Chieh Hung | 11/03
S097 Tainan Rende | South | 1.5 | Display delivery | Hui-Ting Hsiao | 11/04
S104 Keelung Renai | East | 1.5 | Staff roster | Kuan-Ting Lai | 11/04
S113 Yilan Luodong | East | 1.5 | Display delivery | Pei-Shan Shih | 11/04

## Slide 6
Risks and action items
Zava Retail
Zava Anniversary Sale Campaign war room deck Internal use only
6
# | Action | Owner | Due | Status
1 | POS pricing report-back from three top-10 stores | Regional Operations | 10/30 | In progress
2 | Track display delivery in the South (3 stores) | South supervisor | 11/03 | In progress
3 | Staffing support for the East | East supervisor | 11/04 | Not started
4 | Final check before pricing cut-off | Pricing Governance | 11/03 18:00 | Not started
5 | Chain-wide shelf check the day before launch | Regional Operations | 11/05 | Not started
Key risks: late pricing means stores sell at old prices; South display delivery depends on the 11/02 delivery batch.

## Slide 7
Decisions (previous war room)
Zava Retail
Zava Anniversary Sale Campaign war room deck Internal use only
7
1. The top-10 stores by revenue must be fully prepared before launch (decided by Ming-Che Tsai, Regional Director)
2. Readiness is refreshed every Monday and Thursday, consolidated by Regional Operations
3. No exceptions after the pricing cut-off (2026-11-03 18:00); urgent changes need Director approval
4. Not-ready stores must submit a recovery plan and name an owner

## Slide 8
Next two weeks
Zava Retail
Zava Anniversary Sale Campaign war room deck Internal use only
8
Date | Event | Note
10/30 (Fri) | Top-10 store pricing report-back | Escalate immediately if late
11/03 (Tue) | POS pricing cut-off 18:00 | T-3
11/05 (Thu) | Chain-wide shelf check | T-1
11/06 (Fri) | Anniversary Sale launch | T