Anniversary War Room  Meeting Minutes (No. 2)

| Doc. No. | Version | Effective | Owner |
| --- | --- | --- | --- |
| ZR-RO-MIN-2610-02 | v1.0 | 2026-10-05 | Regional Operations |

# 1. Meeting details

| Item | Detail |
| --- | --- |
| Date / time | 2026-10-05 10:00–11:00 |
| Venue | Teams online meeting |
| Chair | Ya-Ting Lin, Regional Operations Manager |
| Attendees | Ming-Che Tsai (Regional Director), Pricing Governance, Inventory & Receiving Control, North / Central / South / East supervisors |
| Minutes | Regional Operations |

# 2. Decisions

| No. | Decision | Decided by / owner | Note |
| --- | --- | --- | --- |
| D-01 | The top-10 stores by revenue must be fully prepared before launch | Ming-Che Tsai, Regional Director | Covers POS pricing, display, staffing and stock |
| D-02 | Readiness refreshed every Monday and Thursday, consolidated by Regional Operations; overall readiness threshold stays at 90% | Ya-Ting Lin |  |
| D-03 | POS pricing cut-off is 3 days before launch (T-3) 18:00 (2026-11-03); no exceptions afterwards, urgent changes need Director approval | Ming-Che Tsai, Regional Director | Later changes miss the weekend batch |
| D-04 | Not-ready stores must submit a recovery plan and name an owner | Area supervisors | Report back at the next war room |
| D-05 | Inventory & Receiving Control tracks the first batch of featured products (Food Storage Set, Storage Basket) to stores | Inventory & Receiving Control |  |

# 3. Action items

| No. | Action | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| A-01 | Report POS pricing progress for three top-10 stores | Regional Operations | 2026-10-30 | In progress |
| A-02 | Confirm South display delivery arrival date | South supervisor | 2026-11-03 | In progress |
| A-03 | Staffing support plan for the East | East supervisor | 2026-11-04 | Not started |
| A-04 | Finalise the chain-wide shelf check form | Regional Operations | 2026-11-02 | Not started |

# 4. Next meeting

War Room No. 3: 2026-10-19 (Mon) 10:00–11:00. Agenda follows these decisions and the latest readiness tracker.