## Readiness Detail
Zava Anniversary Sale Store Readiness Tracker
Doc. ZR-RO-TRK-2610 Data as of 2026-10-12 Owner: Regional Operations Launch 2026-11-06
Store ID | Store | Region | Forecast campaign revenue (NTD million) | POS pricing | Display delivery | Staff roster | Stock in place | Overall status | Owner | Target completion | Notes
S001 | Pingtung Donggang | South | 2.6 | Done | Done | Done | Done | Ready | Kuo-Hao Tseng | 2026-10-07 | Posters installed
S002 | Hualien Yuli | East | 2.6 | Done | Done | Done | Done | Ready | Yi-Hsuan Chiang | 2026-10-05
S003 | Taipei Xinyi | North | 30 | Done | Done | Done | Done | Ready | Po-Han Fang | 2026-10-07 | New hires trained
S004 | Kaohsiung Luzhu | South | 2.6 | Done | Done | Done | Done | Ready | Fang-Yu Yeh | 2026-10-08
S005 | Taichung Fengjia | Central | 2.6 | Done | Done | Done | Done | Ready | Tzu-Hao Kao | 2026-10-05
S006 | Kaohsiung Yanchao | South | 2.6 | Done | Done | Done | Done | Ready | Wan-Ju Pan | 2026-10-09
S007 | Banqiao | North | 25 | Done | Done | Done | Done | Ready | Li-Wei Chien | 2026-10-08
S008 | Zhonghe Jingan | North | 20 | In progress | Done | Done | Done | Not ready | Chia-Jung Li | 2026-10-30 | Waiting for price file confirmation
S009 | Taoyuan Yiwen | Central | 2.6 | Done | Done | Done | Done | Ready | Ya-Hui Shen | 2026-10-03
S010 | Kaohsiung Sanmin | South | 2.6 | Done | Done | Done | Done | Ready | Chun-Ting Ting | 2026-10-05
S011 | Taichung Xitun | Central | 26 | Done | Done | Done | Done | Ready | Shu-Yuan Kang | 2026-10-09
S012 | Changhua City | Central | 2.6 | Done | Done | Done | Done | Ready | Chih-Ming Wang | 2026-10-04 | Posters installed
S013 | Yonghe Dingxi | North | 2.6 | Done | Done | Done | Done | Ready | Chia-Jung Li | 2026-10-10
S014 | Taipei Beitou | North | 22 | In progress | Done | Done | Done | Not ready | Chih-Ming Wang | 2026-10-30 | Waiting for price file confirmation
S015 | Shenkeng | North | 2.6 | Done | Done | Done | Done | Ready | Chien-Hung Chou | 2026-10-09
S016 | Keelung Qidu | East | 2.6 | Done | Done | Done | Done | Ready | Yi-Ting Kuo | 2026-10-10 | Price file returned and checked
S017 | Taichung Dongshi | Central | 2.6 | Done | Done | Done | Done | Ready | Wen-Chieh Hsu | 2026-10-04
S018 | Nantou Caotun | Central | 2.6 | Done | Done | Done | Done | Ready | Ya-Wen Cheng | 2026-10-06
S019 | Xinzhuang | North | 24 | Done | Done | Done | Done | Ready | Ming-Chieh Hung | 2026-10-03
S020 | Tainan Anping | South | 2.6 | Done | Done | Done | Done | Ready | Hui-Ting Hsiao | 2026-10-05
S021 | Keelung Anle | East | 2.6 | Done | Done | Done | Done | Ready | Kuan-Ting Lai | 2026-10-04
S022 | Hualien Xincheng | East | 2.6 | Done | Done | Done | Done | Ready | Pei-Shan Shih | 2026-10-05 | New hires trained
S023 | Banqiao Jiangzicui | North | 2.6 | Done | Done | Done | Done | Ready | Kuo-Hao Tseng | 2026-10-02
S024 | Kaohsiung Gangshan | South | 2.6 | Done | Done | Done | Done | Ready | Yi-Hsuan Chiang | 2026-10-12
S025 | Chiayi Minxiong | South | 23 | Done | Done | Done | Done | Ready | Po-Han Fang | 2026-10-11 | Manager rotation, handover done
S026 | Taipei Zhongshan | North | 2.6 | Done | Done | Done | Done | Ready | Fang-Yu Yeh | 2026-10-10
S027 | Hsinchu Zhubei | Central | 2.6 | Done | Done | Done | Done | Ready | Tzu-Hao Kao | 2026-10-07
S028 | Yingge | North | 2.6 | Done | Done | Done | Done | Ready | Wan-Ju Pan | 2026-10-10
S029 | Tamsui New Town | North | 2.6 | Done | Done | Done | Done | Ready | Li-Wei Chien | 2026-10-03
S030 | Taichung Wuri | Central | 2.6 | Done | Done | Done | Done | Ready | Ya-Hui Shen | 2026-10-12
S031 | Taipei Neihu | North | 21 | Done | Done | Done | Done | Ready | Chun-Ting Ting | 2026-10-04
S032 | Taoyuan Pingzhen | Central | 2.6 | Done | Done | Done | Done | Ready | Shu-Yuan Kang | 2026-10-02
S033 | Taitung Zhiben | East | 2.6 | Done | Done | Done | Done | Ready | Chih-Ming Wang | 2026-10-02 | Display kits received
S034 | Taichung Dali | Central | 2.6 | Done | Done | Done | Done | Ready | Chia-Jung Li | 2026-10-04 | Chiller layout adjusted
S035 | Ruifang | North | 2.6 | Done | Done | Done | Done | Ready | Chien-Hung Chou | 2026-10-03
S036 | Hualien Fenglin | East | 2.6 | Done | Done | Done | Done | Ready | Yi-Ting Kuo | 2026-10-02 | Weekend overtime roster confirmed
S037 | Xinzhuang Fuduxin | North | 2.6 | Done | Done | Done | Done | Ready | Wen-Chieh Hsu | 2026-10-10
S038 | Taipei Datong | North | 2.6 | Done | Done | Done | Done | Ready | Ya-Wen Cheng | 2026-10-07
S039 | Taitung City | East | 2.6 | Done | Done | Done | Done | Ready | Ming-Chieh Hung | 2026-10-02
S040 | Kaohsiung Fengshan | South | 2.6 | Done | Done | Done | Done | Ready | Hui-Ting Hsiao | 2026-10-10
S041 | Chiayi Puzi | South | 2.6 | Done | Done | Done | Done | Ready | Kuan-Ting Lai | 2026-10-03
S042 | Yunlin Xiluo | South | 19 | Done | Done | Done | Done | Ready | Pei-Shan Shih | 2026-10-12 | Weekend overtime roster confirmed
S043 | Yilan Jiaoxi | East | 2.6 | Done | Done | Done | Done | Ready | Kuo-Hao Tseng | 2026-10-08
S044 | Hualien City | East | 2.6 | Done | Done | Done | Done | Ready | Yi-Hsuan Chiang | 2026-10-06
S045 | Miaoli Toufen | Central | 2.6 | Done | Done | Done | Done | Ready | Po-Han Fang | 2026-10-06 | Display kits received
S046 | Kaohsiung Lingya | South | 2.6 | Done | Done | Done | Done | Ready | Fang-Yu Yeh | 2026-10-10
S047 | Taishan | North | 2.6 | Done | Done | Done | Done | Ready | Tzu-Hao Kao | 2026-10-09
S048 | Sanxia | North | 2.6 | Done | Done | Done | Done | Ready | Wan-Ju Pan | 2026-10-05
S049 | Penghu Magong | East | 2.6 | Done | Done | Done | Done | Ready | Li-Wei Chien | 2026-10-12
S050 | Hsinchu East District | Central | 2.5 | Done | Done | Done | Done | Ready | Ya-Hui Shen | 2026-10-09 | Weekend overtime roster confirmed
S051 | Xindian | North | 2.5 | Done | Done | Done | Done | Ready | Chun-Ting Ting | 2026-10-07
S052 | Taipei Songshan | North | 2.5 | Done | Done | Done | Done | Ready | Shu-Yuan Kang | 2026-10-07 | Posters installed
S053 | Luzhou | North | 2.5 | Done | Done | Done | Done | Ready | Chih-Ming Wang | 2026-10-04
S054 | Yonghe | North | 2.5 | Done | Done | Done | Done | Ready | Chia-Jung Li | 2026-10-04
S055 | Linkou | North | 2.5 | Done | Done | Done | Done | Ready | Chien-Hung Chou | 2026-10-08
S056 | Taichung Fengyuan | Central | 18 | Not started | Done | Done | Done | Not ready | Chien-Hung Chou | 2026-11-02 | Waiting for price file confirmation
S057 | Shulin | North | 2.5 | Done | Done | Done | Done | Ready | Yi-Ting Kuo | 2026-10-09
S058 | Kinmen Jincheng | East | 2.5 | Done | Done | Done | Done | Ready | Wen-Chieh Hsu | 2026-10-07
S059 | Yilan City | East | 2.5 | Done | Done | Done | Done | Ready | Ya-Wen Cheng | 2026-10-08
S060 | Xizhi | North | 2.5 | Done | Done | Done | Done | Ready | Ming-Chieh Hung | 2026-10-05
S061 | Taoyuan Bade | Central | 2.5 | Done | Done | Done | Done | Ready | Hui-Ting Hsiao | 2026-10-02 | Display kits received
S062 | Sanchong | North | 2.5 | Done | Done | Done | Done | Ready | Kuan-Ting Lai | 2026-10-03 | Chiller layout adjusted
S063 | Bali | North | 2.5 | Done | Done | Done | Done | Ready | Pei-Shan Shih | 2026-10-10
S064 | Taichung Shalu | Central | 2.5 | Done | Done | Done | Done | Ready | Kuo-Hao Tseng | 2026-10-07
S065 | Zhonghe | North | 2.5 | Done | Done | Done | Done | Ready | Yi-Hsuan Chiang | 2026-10-03
S066 | Hsinchu Xinpu | Central | 2.5 | Done | Done | Done | Done | Ready | Po-Han Fang | 2026-10-10
S067 | Taoyuan Zhongli | Central | 2.5 | Done | Done | Done | Done | Ready | Fang-Yu Yeh | 2026-10-04
S068 | Taipei Shilin | North | 2.5 | Done | Done | Done | Done | Ready | Tzu-Hao Kao | 2026-10-06
S069 | Taipei Daan | North | 2.5 | Done | Done | Done | Done | Ready | Wan-Ju Pan | 2026-10-05
S070 | Taichung Beitun | Central | 2.5 | Done | Done | Done | Done | Ready | Li-Wei Chien | 2026-10-06
S071 | Tainan Jiali | South | 1.5 | Done | In progress | Done | Done | Not ready | Yi-Ting Kuo | 2026-11-03 | Delivery batch not yet at store
S072 | Tamsui | North | 2.5 | Done | Done | Done | Done | Ready | Ya-Hui Shen | 2026-10-06
S073 | Tainan Yongkang | South | 2.5 | Done | Done | Done | Done | Ready | Chun-Ting Ting | 2026-10-12 | Weekend overtime roster confirmed
S074 | Wugu | North | 2.5 | Done | Done | Done | Done | Ready | Shu-Yuan Kang | 2026-10-02
S075 | Taitung Guanshan | East | 2.5 | Done | Done | Done | Done | Ready | Chih-Ming Wang | 2026-10-06
S076 | Yunlin Huwei | South | 2.5 | Done | Done | Done | Done | Ready | Chia-Jung Li | 2026-10-04
S077 | Yunlin Douliu | South | 2.5 | Done | Done | Done | Done | Ready | Chien-Hung Chou | 2026-10-02
S078 | Kaohsiung Zuoying | South | 1.5 | Done | Done | In progress | Done | Not ready | Wen-Chieh Hsu | 2026-11-03 | Roster pending area supervisor approval
S079 | Taoyuan Luzhu | Central | 2.5 | Done | Done | Done | Done | Ready | Yi-Ting Kuo | 2026-10-04 | Weekend overtime roster confirmed
S080 | Taichung Tanzi | Central | 2.5 | Done | Done | Done | Done | Ready | Wen-Chieh Hsu | 2026-10-09
S081 | Hsinchu Guangfu | Central | 2.5 | Done | Done | Done | Done | Ready | Ya-Wen Cheng | 2026-10-12
S082 | Taipei Nangang | North | 2.5 | Done | Done | Done | Done | Ready | Ming-Chieh Hung | 2026-10-12
S083 | Chiayi City | South | 1.5 | Done | Not started | Done | Done | Not ready | Ya-Wen Cheng | 2026-11-04 | Delivery batch not yet at store
S084 | Taichung Qingshui | Central | 2.5 | Done | Done | Done | Done | Ready | Hui-Ting Hsiao | 2026-10-02 | New hires trained
S085 | Changhua Lukang | Central | 2.5 | Done | Done | Done | Done | Ready | Kuan-Ting Lai | 2026-10-09 | New hires trained
S086 | Changhua Yuanlin | Central | 2.5 | Done | Done | Done | Done | Ready | Pei-Shan Shih | 2026-10-12
S087 | Yilan Wujie | East | 2.5 | Done | Done | Done | Done | Ready | Kuo-Hao Tseng | 2026-10-02
S088 | Pingtung Hengchun | South | 2.5 | Done | Done | Done | Done | Ready | Yi-Hsuan Chiang | 2026-10-11 | Manager rotation, handover done
S089 | Taichung Nantun | Central | 2.5 | Done | Done | Done | Done | Ready | Po-Han Fang | 2026-10-07
S090 | Kaohsiung Daliao | South | 1.5 | In progress | Done | Done | Done | Not ready | Ming-Chieh Hung | 2026-11-03 | Waiting for price file confirmation
S091 | Nantou City | Central | 2.5 | Done | Done | Done | Done | Ready | Fang-Yu Yeh | 2026-10-07
S092 | Tainan East District | South | 2.5 | Done | Done | Done | Done | Ready | Tzu-Hao Kao | 2026-10-05 | Display kits received
S093 | Taipei Wanhua | North | 2.5 | Done | Done | Done | Done | Ready | Wan-Ju Pan | 2026-10-10
S094 | Tucheng | North | 2.5 | Done | Done | Done | Done | Ready | Li-Wei Chien | 2026-10-09
S095 | Pingtung City | South | 2.5 | Done | Done | Done | Done | Ready | Ya-Hui Shen | 2026-10-05 | Posters installed
S096 | Pingtung Chaozhou | South | 2.5 | Done | Done | Done | Done | Ready | Chun-Ting Ting | 2026-10-08
S097 | Tainan Rende | South | 1.5 | Done | Not started | Done | Done | Not ready | Hui-Ting Hsiao | 2026-11-04 | Delivery batch not yet at store
S098 | Kaohsiung Renwu | South | 2.5 | Done | Done | Done | Done | Ready | Shu-Yuan Kang | 2026-10-09 | Manager rotation, handover done
S099 | Taipei Wenshan | North | 2.5 | Done | Done | Done | Done | Ready | Chih-Ming Wang | 2026-10-06
S100 | Xindian Zhongyang | North | 2.5 | Done | Done | Done | Done | Ready | Chia-Jung Li | 2026-10-12 | Chiller layout adjusted
S101 | Taichung Taiping | Central | 2.5 | Done | Done | Done | Done | Ready | Chien-Hung Chou | 2026-10-05 | Posters installed
S102 | Hualien Jian | East | 2.5 | Done | Done | Done | Done | Ready | Yi-Ting Kuo | 2026-10-02
S103 | Taipei Zhongzheng | North | 2.5 | Done | Done | Done | Done | Ready | Wen-Chieh Hsu | 2026-10-11
S104 | Keelung Renai | East | 1.5 | Done | Done | In progress | Done | Not ready | Kuan-Ting Lai | 2026-11-04 | Roster pending area supervisor approval
S105 | Tainan Xinying | South | 2.5 | Done | Done | Done | Done | Ready | Ya-Wen Cheng | 2026-10-04 | Manager rotation, handover done
S106 | Kaohsiung Nanzi | South | 2.5 | Done | Done | Done | Done | Ready | Ming-Chieh Hung | 2026-10-06
S107 | Yilan Suao | East | 2.5 | Done | Done | Done | Done | Ready | Hui-Ting Hsiao | 2026-10-10
S108 | Tucheng Yumin | North | 2.5 | Done | Done | Done | Done | Ready | Kuan-Ting Lai | 2026-10-11
S109 | Linkou Wenhua | North | 2.5 | Done | Done | Done | Done | Ready | Pei-Shan Shih | 2026-10-12 | Manager rotation, handover done
S110 | Miaoli City | Central | 2.5 | Done | Done | Done | Done | Ready | Kuo-Hao Tseng | 2026-10-07 | Posters installed
S111 | Taoyuan Guishan | Central | 2.5 | Done | Done | Done | Done | Ready | Yi-Hsuan Chiang | 2026-10-08
S112 | Tainan Madou | South | 2.5 | Done | Done | Done | Done | Ready | Po-Han Fang | 2026-10-07
S113 | Yilan Luodong | East | 1.5 | Done | In progress | Done | Done | Not ready | Pei-Shan Shih | 2026-11-04 | Delivery batch not yet at store
S114 | Changhua Hemei | Central | 2.5 | Done | Done | Done | Done | Ready | Fang-Yu Yeh | 2026-10-08
S115 | Yilan Toucheng | East | 2.5 | Done | Done | Done | Done | Ready | Tzu-Hao Kao | 2026-10-03
S116 | Tainan Shanhua | South | 2.5 | Done | Done | Done | Done | Ready | Wan-Ju Pan | 2026-10-06 | Manager rotation, handover done
S117 | Kaohsiung Qianzhen | South | 2.5 | Done | Done | Done | Done | Ready | Li-Wei Chien | 2026-10-11
S118 | Kaohsiung Xiaogang | South | 2.5 | Done | Done | Done | Done | Ready | Ya-Hui Shen | 2026-10-02 | Chiller layout adjusted
S119 | Keelung Zhongshan | East | 2.5 | Done | Done | Done | Done | Ready | Chun-Ting Ting | 2026-10-05 | Display kits received
S120 | Sanchong Chongxin | North | 2.5 | Done | Done | Done | Done | Ready | Shu-Yuan Kang | 2026-10-09

## Summary
Readiness Summary
Data as of 2026-10-12 Formula-driven
Item | Value | Note
Total stores
Ready stores |  | POS pricing, display, staffing and stock all complete
Not-ready stores
Readiness (ready ÷ total stores)
Readiness threshold | 90% | Set by the war room
Threshold met?
Region | Stores | Ready | Not ready | Readiness
North
Central
South
East

## Field Notes
Field notes and revision history
Field | Description
POS pricing | Campaign price file is live on POS and spot-checked
Display delivery | Campaign display kits and posters have arrived at the store
Staff roster | Rosters for the two weeks around launch are approved
Stock in place | First batch of featured products is on the shelf
Overall status | 'Ready' only when all four items are 'Done'
Target completion | Actual completion date for ready stores; committed date for not-ready stores
Version | v1.3 2026-10-12 updated by Regional Operations