## Slot options
Option | Start | End | Duration (days) | Flights cancelled | Facility
Option A | 2026-10-13 | 2026-10-26 | 14 | 14 | Taoyuan in-house hangar, Bay 2
Option B | 2026-11-02 | 2026-11-15 | 14 | 22 | Taoyuan in-house hangar, Bay 2
Option C | 2026-10-25 | 2026-11-07 | 14 | 19 | Taoyuan in-house hangar, Bay 2

## Resource availability
Resource | Blocked from | Blocked to | Held by | Note
Taoyuan in-house hangar, Bay 2 | 2026-10-10 | 2026-10-24 | B-99204 | NW-220 fleet C check
Contoso Aero Services | 2026-10-12 | 2026-10-30 | — | Slot book full; no insertions accepted